## Example Schedule
Description and Instructions: This master checklist provides guidance for outreach events. To begin, populate your "Event Date" into cell C2 below (for example, 4/27/22) and the formulas will calculate the target date to complete the action items.
Enter Event Date Here
Status | Volunteer Leader | Action Items and Resources | Days Out | Target Date | Recommendations
90 DAYS PRIOR TO EVENT
Not Started | Event Manager | Select a theme or general program idea | 90 | #VALUE!
Not Started | Event Manager | Select a date for the program | 90 | #VALUE!
Not Started | Event Manager | Select Event Managers | 90 | #VALUE! | This should be at least 2 and no more than 4 people. Be sure to assign an overall manager as well. Refer to the Roles and Responsibilities tool for a description.
Not Started | Event Manager | Create a regular meeting schedule | 90 | #VALUE! | Telecoms with leadership team and local meetings with leads should be planned for the span of the event. It is recommended that Lead Volunteers meet every other week via phone or in person during the first 90 days and then every week 30 days prior to the event. Also, plan your volunteer training sessions within one the week of the event. Consider having it at or near the event site so everyone is clear on where they need to go the day of the event. Use this document to guide your Lead Volunteer Meeting.
Not Started | Event Manager | Decide on a single email contact for the event. | 90 | #VALUE! | Consider making a section-specific outreach email. If you would like a SWE email, please email SWE at hq@swe.org.
Not Started | Event Manager | Venue - Scout and secure a venue for your event | 90 | #VALUE! | A college campus is a great location if available. It can also provide additional volunteers and resources. Additional locations for consideration include: libraries, museums, companies, convention centers, and event halls. When selecting a venue ensure that there is sufficient space for registration, a main gathering room, and break-out rooms for students and parent. Try to keep all room locations in close proximity. An alternative is to do all activities in a single large room. Video conferencing services like Zoom, Teams, etc. can be great options for virtual events and have the option to split students and volunteers into break out rooms.
Not Started | Event Manager | Event Managers select leadership team including coordinators and leads | 90 | #VALUE! | Refer to the Event Planning Roles and Checklist
Not Started | Activities Coordinator | Select activities to use during your event. | 90 | #VALUE! | Refer to the links in the Activity Selection Resources worksheet to begin investigating activities for your event.
Not Started | Recruitment & Publicity Coordinator | Create a girl recruiting plan/advertising and media plan | 90 | #VALUE! | Take advantage of existing relationship with organizations like Girl Scouts, Girls Inc., 4H, National Girls Collaborative Project, WGBH, FIRST, AISES, NESBE, SHPE and museums. We recommend telling them no later than 90 days before. Additional options include social media, news broadcasts, newspapers , magazines, and radio.
Not Started | Safety and Management Coordinator | Download Insurance Coverage Questionnaire – located within SWE Resources. | 90 | #VALUE! | Some special events are included in SWE’s coverage and other special events may require an additional premium. Refer to the questionnaire guidelines to learn more.
75-80 DAYS PRIOR TO EVENT
Not Started | Parents and Educator Program (PEP) Coordinator | Select inspirational & engaging speaker(s) to speak about engineering & the challenges faced by females today for the Parent Educator Program (PEP) event | 80 | #VALUE! | Strong speakers can speak to: collegiate experience, professional experience, college admissions, industry leaders, K-12 Educators, etc. The strongest panels represent diversity of age and ethnicity.
Also refer to the Panel Questions resource
Not Started | Recruitment & Communication Coordinator | Registration - create online registration page | 75 | #VALUE! | Using an electronic registration system provides many benefits. Popular options are Eventbrite and Google/Microsoft Forms. Provide a map for parking and a drawn path for attendees to follow to ensure they get to the right place on the day of the event. If you are providing food or t-shirts, don't forget to include an option to input allergies or dietary restrictions and t-shirt size.
Not Started | Recruitment & Publicity Coordinator | Registration - include permission and photo release forms if applicable. | 75 | #VALUE! | Make sure to add a "file upload" option on the registration to allow parents to upload permission slips or releases.
|  | Permission Form for Minors | 75 | #VALUE!
Student and Parent Educator Program Track Acknowledgement
Student Media Release Form
Adult Photo and Video Release Waiver
Not Started | Recruitment & Publicity Coordinator | Download and complete an Event Flyer. | 75 | #VALUE! | Use the flyer template to get started or make your own!
Not Started | Recruitment & Publicity Coordinator | Provide a press release using the following template. | 90 | #VALUE! | Press releases are not required, but can go a long way to help recruit for the event. Use the template and edit as needed for your event.
Not Started | All volunteer coordinators | Define shifts and roles for your volunteer core and provide to your volunteer coordinator. | 70 | #VALUE! | Each volunteer leader needs to define how many volunteers are needed and the needed shift times. Additional volunteers are optional but should be considered because they are especially helpful with organization, set up, or breaking down. Examples include: university students, professors, administration, professionals, etc.
60 DAYS PRIOR TO EVENT
Not Started | Volunteer Coordinator | Create and management volunteer shifts and schedules. | 60 | #VALUE! | Popular ways to organize shifts are https://signup.com/MySignUp, https://www.volunteerlocal.com/, https://www.signupgenius.com/, or an web-editable Excel like Google Sheets.
Not Started | Recruitment & Publicity Coordinator | Open registration | 60 | #VALUE! | Registration can be opened earlier, but no later than 60 days before the event. Advertise registration on your section's calendar/newsletter/blog, with schools and other local youth organizations, on social media, with employers, and more!
45 DAYS PRIOR TO EVENT
Not Started | Materials Coordinator | Order identified materials | 45 | #VALUE! | It is often easier to order pre-made kits than have students grab individual supplies. Make sure kits have all components before the event. If ordering individual supplies, look online for the best prices. Practice the activities at least once before the day of the event using a pre-made kit.
Not Started | Materials Coordinator | Order give aways/gifts for attendees | 60 | #VALUE! | Consider t-shirts for volunteers and/or participants and goodie bags for participants. Branded table cloths or signage are also attention grabbing and helpful for students and parents to recognize where to go the day of.
30 DAYS PRIOR TO EVENT
Not Started | Food Coordinator | Select and order snacks and/or lunch | 30 | #VALUE! | You can also have students bring a lunch to decrease costs and avoid potential issues with allergies or dietary restrictions.
Not Started | Event Manager | Create a schedule/agenda for the event for all attendees (Girls and PEP) | 30 | #VALUE! | A master schedule should be available to all event managers, activities leads, the PEP Coordinator, and volunteers. The schedule should be highlighted at the opening of your event.
Not Started | Recruitment & Publicity Coordinator | Download Certificate-of-Completion template. | 30 | #VALUE! | Certificates are optional but if you do use them, be creative by adding pictures, logos, etc. You may even want to consider emailing this to the girls after the event.
Not Started | Opening Activity Team Lead | Plan the opening activity of the event | 30 | #VALUE! | The opening activity should be open ended to accommodate the first girl who arrives as well as the last girl who arrives. Make sure it is something they can start whenever they get there, it can be done with limited instruction, and won't interfere with your starting on time.
Not Started | Registration & Dismissal Coordinator | Create sign-in and check-out table plan for girls, PEP, and volunteers | 30 | #VALUE! | There should be 3 sign in areas. 1) for the girls, 2) for the Parents and Educators and 3) for the volunteers. With 200 girls we recommend having 6 lines divided by last name. The actual letter division should be based on actual names and then the divisions should be made evenly. In the PEP sign in area 3-4 lines by last name is sufficient. Volunteer registration is a place for volunteers to check in. Check-in tables are the place to distribute name tags, t-shirts, goodie bags, etc.
Not Started | Safety & Management Coordinator | Emergency plan and materials | 30 | #VALUE! | Most campus venues have security. The Safety Coordinator should work with the venue to find out what first aid and emergency procedures are in place. Having a volunteer with medical training or at least first aid training is always a good idea. Having a basic first aid kit is a minimum requirement. The Safety Coordinator should know where all sign-in information is in case a parent needs to be contacted. If an evacuation becomes necessary the Safety coordinator is responsible for ensuring that our group leaves in a coordinated manor.
Not Started | Event Reporter | Photos and videos | 30 | #VALUE! | It is recommended that a few volunteers are asked to fill this role before the event. Other volunteers should take pictures/video on their personal devices. Ask volunteers to send their photos/videos to the event managers using the event email. If it is within budget, you may even consider a professional photographer.
2 WEEKS PRIOR TO EVENT
Not Started | Assessment Coordinator | Develop surveys for students | 14 | #VALUE! | Depending on the age group, students may not write an extensive amount on their survey. Consider questions that ask students to draw their experience like "Draw your favorite part of the day" or have them choose options on a number scale.
Not Started | Assessment Coordinator | Develop surveys for parents | 14 | #VALUE!
Not Started | Assessment Coordinator | Complete surveys for volunteers | 14 | #VALUE!
Not Started | Safety & Management Coordinator | Plan the layout and then create/print signage as needed | 14 | #VALUE! | Signage should help participants find the location, know where to park, and know where the event is taking place.
Not Started | Volunteer Coordinator | Lead volunteers in Role Models Matter training on the SWE Advanced Learning Center | 14 | #VALUE! | Encourage volunteers to complete the free training on the ALC
Not Started | Volunteer Coordinator | Hands-on volunteer training and/or briefing | 14 | #VALUE! | You can also train the volunteers in the activity an hour or more before the event. Doing it prior to the day of allows for more buffer to make adjustments to the activity, have volunteers stuff goodie bags, or assist with other preparation.
1 WEEK PRIOR TO EVENT
Not Started | Registration & Dismissal Coordinator | Close registration | 7 | #VALUE! | Registration may stay open beyond seven days before the event if additional registrants are needed.
Not Started | Registration & Dismissal Coordinator | Girl and PEP, volunteer communications: one week out email | 7 | #VALUE! | Reminder 1 - should go to parents, volunteers, and speakers and include any final details including the event location and directions. Be sure to include any special instructions.
Not Started | Registration & Dismissal Coordinator | Girl PEP and volunteer communications: three day out email | 3 | #VALUE! | Reminder 2 should include: directions, special instructions and a reminder to notify event managers if their plans have changed. They should go to parents, volunteers, and speakers.
Not Started | Registration & Dismissal Coordinator | Determine where signs should go | 3 | #VALUE! | Thinking through the placement of signs should be done as early as possible, but actual sign placement will usually happen the evening before or the day of the event.
Not Started | Registration & Dismissal Coordinator | Girl PEP and volunteer communications: one day out email | 1 | #VALUE! | Reminder 3 - should include: directions, special instructions, and a reminder to notify event managers if their plans have changed. They should go to parents, volunteers, and speakers.
DAY OF EVENT
Not Started | Assessment & Post Event Follow-Up Coordinator | Distribute and collect post-event surveys from participants | 0 | #VALUE! | Be sure to schedule time at the end of the event for the attendees to fill out the post-event survey. Hard copies are provided to most attendees. The volunteer surveys may be sent via email. Consider emailing a survey to parents after the event as well - sometimes you'll get some great stories about what their girls told them about the event on the drive home!
Not Started | Materials Coordinator | Day of event set-up and clean-up | 0 | #VALUE! | Access the venue as early as possible. Consider setup the day before. Be prepared to handle trash and recycling. Be sure to have a facilities contact that can help with building issues. Be sure that you have volunteers in shifts to post event cleanup.
Not Started | Materials Coordinator | Prepare and organize a supply station | 0 | #VALUE! | The Supply Station is the designated drop spot for all supplies that require distribution or are there for common use. Feedback from previous events suggests that providing a single well organized location helps a great deal with efficiency. Consider having a volunteer responsible for this station.
AFTER THE EVENT
Not Started | Assessment & Post Event Follow-Up Coordinator | Send out post event surveys to volunteers | -2 | #VALUE! | Although paper versions could be provided at the event, it is best when we can collect responses via an online survey
Not Started | Assessment Coordinator | Complete the Outreach Metric Tool | -2 | #VALUE!
Not Started | Event Reporter | Post pictures and videos to section social media | -5 | #VALUE! | Post event pictures on social media!
Not Started | Event Reporter | Send post event article to SWE for publication (optional) | -5 | #VALUE!
Not Started | Assessment & Post Event Follow-Up Coordinator | Send a thank you to all volunteers, speakers, and attendees | -5 | #VALUE!

## Activity Selection Resources
Use the following links to select activities for your event.
Design Squad: www.pbskids.org/designsquad
Techbridge: www.techbridgegirls.org
HowToSmile.Org
Teach Engineering - Teachengineering.org/browse_activities.php
https://hourofcode.com/us/learn
https://code.org/learn

## Sheet2 (hidden)
Not Started
In Progress
Complete

## Leadership Worksheet
This is a worksheet. Please add cells notes and new jobs as needed.
Volunteer Leadership | Name of Lead | Phone Number 1 | Email
Event Manager 1
Event Manager 2
Recruitment and Publicity Coordinator
Food Coordinator
Activities Coordinator
Volunteer Coordinator
Materials Coordinator
Girl /PEP Registration and Dismissal Coordinator
Treasury Coordinator
Assessment and Post Event Activity Coordinator
Parent Educator (PEP) Coordinator
Saftey Coordinator
EXPO Coordinator
Facilities Coordinator
Environment Coordinator
Facilitator/MC

## Example Budget
Total Budget for supplies:
Event Name
Activity Name
Purpose | Item | Quantity Needed | Price/Item | Total
0
0
0
0
0
0
0
0
0
0
|  |  | Total | 0
|  |  | Number of kits you can make with budget: | #DIV/0!